## ProjectTeam
Name | GitHub Alias
Quentin Chiquet | QuentinChiquet
Gabor Tanz | izolight
Joel Von Almen | sheggi
Nic Dorner | spiderpig36
Ken Letander | kenboy192
Hannes Rodel | hdrodel

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Add an Appointment | The user adds an appointment | high |  |  | 0h | waiting
2 | View appointment | User selects appointment to get displayed | medium |  |  | 0h | waiting
3 | Complete appointment | user marks appointment as done | low |  |  | 0h | waiting
4 | manage patient data | user updates patient data | high |  |  | 0h | waiting
5 | organise appointment | user changes appointment information | medium |  |  | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Database setup |  | Database | Gabor | Quentin | High | 7 |  |  | waiting
1.2 | 1 | Interface to Database |  | Database | Quentin | Gabor | High | 7 |  |  | waiting
1.3 | 1 | Appointment veiw |  | UI, Controller | Hannes | Nic | high | 7 |  |  | waiting
1.4 | 1 | Make Calendar |  | UI, Controller | Nic | Hannes | high | 7 |  |  | waiting
1.5 | 1 | Login view |  | UI, Controller | Ken | Joel | high | 7 |  |  | waiting
1.6 | 1 | Login Backend |  | Database | Joel | Ken | high | 7 |  |  | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180