## ProjectTeam
Name | GitHub Alias
Quentin Chiquet | QuentinChiquet
Gabor Tanz | izolight
Joel Von Almen | sheggi
Nic Dorner | spiderpig36
Ken Letander | kenboy192
Hannes Rodel | hdrodel

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Add an Appointment | The user adds an appointment | medium | 10 |  | 7 | In Progress
2 | View appointment | User selects appointment to get displayed | high | 20 | 40 | 31 | In Progress
3 | Complete appointment | user marks appointment as done | low | 7 |  | 0h | waiting
4 | manage patient data | user updates patient data | high | 16 |  | 0h | waiting
5 | organise appointment | user changes appointment information | medium | 11 |  | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Database setup |  | Database | Gabor | Quentin | High | 7 | 7 | 7 | Done
1.2 | 1 | Interface to Database |  | Database | Quentin | Gabor | High | 7 | 7 | 7 | Done
1.3 | 1 | Appointment veiw |  | UI, Controller | Hannes | Nic | High | 7 | 10 | 7 | Moved
1.4 | 1 | Make Calendar |  | UI, Controller | Nic | Hannes | High | 7 | 7 | 3 | Moved
1.5 | 1 | Login view |  | UI, Controller | Ken | Joel | High | 7 | 7 | 7 | Done
1.6 | 1 | Login Backend |  | Database | Joel | Ken | High | 7 | 7 | 7 | Done
2.1 | 2 | Make Calendar |  | UI, Controller | Nic | Hannes | High | 7 | 7 | 7 | Done
2.2 | 2 | Appointment veiw |  | UI, Controller | Nic | Hannes | High | 7 | 10 | 10 | Done
2.3 | 2 | Patient Information view → Tab Todo |  | UI, Controller | Ken | Joel | High | 10 | 14 | 10 | In Progress
2.4 | 2 | Menu integration |  | UI, Controller | Ken | Joel | High | 4 | 4 | 4 | Done
2.5 | 2 | State pattern |  | Controller | Gabor | Quentin | High | 14 | 14 | 14 | Done
2.6 | 2 | Patient Information view → Tab PatientInformation |  | UI, Controller | Hannes | Nic | High | 14 | 14 | 2 | In Progress
2.7 | 2 | Patient Information view → Tab MediView |  | UI, Controller | Joel | Ken | High | 14 | 14 | 2 | In Progress
2.8 | 2 | Persisence Layer Task |  | Database | Quentin | Gabor | High | 14 | 14 | 14 | Done
3.1 | 3
3
3
3
3
3

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180